## Group Members And Overview
Group Members | Id | Smart Financial Monitoring & Expense Management System
Berkant Aydın | B2280.060078
Khadega Algumaei | B2280.060158 | This project is an intelligent accounting system designed for small businesses, cafés, and retail stores.
Harun Sezer | B2280.060086 | Project Objectives
Eylül Gülin Arpay | B2380.060016
* Improve financial management for small businesses.
* Support decision-making using accurate financial analytics.
* Enable users to monitor daily, weekly, or monthly financial performance.
* Help businesses identify strengths and weaknesses in each financial period.
Problem Statement
* Difficulty tracking income and expenses manually.
* Lack of periodic financial analysis.
* Limited financial visibility for small businesses.
* No alerts when budgets are exceeded.
* Difficulty managing and tracking paper invoices.
Detailed Project Goals
|  | 1. | Register businesses and manage user accounts.
|  | 2. | Categorize expenses into structured groups (Utilities, Salaries, Transport, etc.).
|  | 3. | Record income and expenses by day, week, or month.
|  | 4. | Calculate net profit and loss per period.
|  | 5. | Generate automatic alerts when exceeding budget or facing losses.
|  | 6. | Display visual reports (Pie Charts and Line Charts).
|  | 7. | Export summary and detailed CSV reports including period comparisons.
|  | 8. | Provide archive search by date or selected period.

## Roles Of Group Members
Members | Roles
Berkant Aydın | Backend Developer
Khadega Algumaei | Frontend Developer
Harun Sezer | Tester/QA
Eylül Gülin Arpay | Documentation Specialist

## Timeline
Weekly Contribution Plan
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Berkant: Berkant will design the backend architecture and will define core data models for business, income, and expense management. | Berkant: Berkant will implement the basic backend structure and will develop core financial management classes. | Berkant: Berkant will implement income and expense recording logic and will handle category-based calculations. | Berkant: Berkant will develop time-based filtering logic to support daily, weekly, and monthly analysis. | Berkant: Berkant will integrate OCR functionality to extract expense data from invoice images automatically. | Berkant: Berkant will prepare financial data for visualization and report generation. | Berkant: Berkant will implement budget alerts, loss detection logic, and CSV export functionality. | Berkant: Berkant will finalize backend code, fix integration issues, and optimize system performance.
Khadega: Khadega will prepare initial UI wireframes and will plan the dashboard layout and navigation structure. | Khadega: Khadega will develop the business registration interface and will set up the main application layout. | Khadega: Khadega will develop income and expense input forms and will implement input validation. | Khadega: Khadega will implement period selection controls and will update dashboard data dynamically. | Khadega: Khadega will design the invoice upload interface and will implement OCR result confirmation screens. | Khadega: Khadega will implement pie and line charts for expense distribution and financial trends. | Khadega: Khadega will add export controls, alert notifications, and archive navigation to the UI. | Khadega: Khadega will polish the user interface and prepare the system for demonstration.
Harun: Harun will prepare the initial test strategy and will identify critical system components. | Harun: Harun will review initial backend logic and will prepare test case templates. | Harun: Harun will conduct functional testing on financial calculations and will verify edge cases. | Harun: Harun will test date-based filtering and period transitions. | Harun: Harun will test OCR accuracy using multiple invoice samples. | Harun: Harun will verify chart accuracy and test visual consistency. | Harun: Harun will test alert triggering, CSV accuracy, and archive retrieval. | Harun: Harun will conduct full system testing, regression testing, and prepare the final test report.
Eylül: Eylül will document the project proposal, problem statement, objectives, and system overview. | Eylül: Eylül will prepare the Software Requirements Specification including functional and non-functional requirements. | Eylül: Eylül will prepare use case diagrams and will document system workflows. | Eylül: Eylül will document system design and will prepare data flow diagrams. | Eylül: Eylül will document the OCR module and its role in automated expense tracking. | Eylül: Eylül will document data visualization processes and include UI screenshots. | Eylül: Eylül will document report generation, data storage, and non-functional requirements. | Eylül: Eylül will finalize the project report, prepare presentation slides, and complete the user manual.

## Budget Planning
Budget Planning
Department | Hourly Rate(USD) |  | Estimated Cost(USD) | Total Hours
Project Management |  | $40 - $60/hr | $1,120 - $1,680 | 28 hours
Backend Developer |  | $50 - $80/hr | $1,600 - $2,560 | 32 hours
Frontend Developer |  | $40 - $70/hr | $1,280 - $2,240 | 32 hours
Tester / QA |  | $30 - $50/hr | $960 - $1,600 | 32 hours
Documentation Specialist |  | $25 - $45/hr | $800 - $1,440 | 32 hours
Total : |  |  | $5,760 - $9,520 | 156 Hours